{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":74,"n_cols":47,"rows_kept":74,"merged":[[3,22,4,22],[5,0,6,0],[5,10,6,10],[5,14,6,14],[5,18,6,18],[5,27,6,27],[5,36,6,36],[5,39,6,39],[7,21,8,21],[12,11,13,11],[12,24,13,24],[14,11,26,11],[14,22,15,22],[22,24,23,24],[24,21,25,21],[24,24,25,24],[26,14,26,16],[27,11,33,11],[27,14,27,16],[28,14,28,16],[29,14,29,17],[29,27,29,28],[30,27,30,29],[32,14,32,17],[33,14,33,16],[34,18,35,18],[34,21,35,21],[34,24,35,24],[39,31,40,31],[41,0,42,0],[41,1,42,1],[41,3,42,3],[41,5,42,5],[41,7,42,7],[41,8,42,8],[41,10,42,10],[41,12,42,12],[41,14,42,14],[41,18,42,18],[41,20,42,20],[41,23,42,23],[41,25,42,25],[41,27,42,27],[41,29,42,29],[41,32,42,32],[41,34,42,34],[41,36,42,36],[41,38,42,38],[41,39,42,39],[41,42,42,42],[41,44,42,44],[41,46,42,46],[43,32,44,32],[45,32,46,32],[47,32,48,32],[51,22,52,22],[51,24,52,24],[53,0,54,0],[53,10,54,10],[53,11,54,11],[53,12,54,12],[53,17,54,17],[53,20,54,20],[53,22,54,22],[53,25,54,25],[53,28,54,28],[53,30,54,30],[55,31,56,31],[68,0,69,0],[68,20,69,20],[68,23,69,23],[68,26,69,26],[68,29,69,29],[68,31,69,31],[68,33,69,33],[68,36,69,36],[68,40,69,40],[68,42,69,42],[68,44,69,44],[69,37,69,38]],"flags":["formulas_cached_only"]}
[]
[]
[]
[{"$nulls":22},"（25）"]
[]
["图纸配合",{"$nulls":3},"项目方案概念设计",{"$nulls":5},"⑥","       总体规划方案设计",null,null,"⑿",{"$nulls":3},"⒄",{"$nulls":4},"单体报建图、施工图审查预审",{"$nulls":3},"（39）",{"$nulls":8},"（54）","出各专业竣工图",null,"（58）"]
[{"$nulls":23},"a、防火审批申报表演"]
[{"$nulls":21},"（21）","                       b、初步设计建筑平立剖各专业室内外消防设计"]
[{"$nulls":22},"                     c、总平面图"]
[{"$nulls":22},"                    d、消防设计专篇"]
[{"$nulls":22},"                  e、审定设计方案通知书"]
[]
[{"$nulls":24},"（32）"]
[]
[{"$nulls":22},"（26）"]
[{"$nulls":24},"   a、人防工程施工图（各专业）"]
[{"$nulls":24},"         b、居住区人防规划工程送审单"]
[{"$nulls":21},"                 a、园林现状测绘报告（交区园林局）",null,null,"             c、人防结构计算表"]
[{"$nulls":21},"                  b、建筑剖面图",null,null,"                  d、人防工程送审单"]
[{"$nulls":21},"                  c、首层、？？及地下各层平面图",null,null,"                       e、地勘资料及地形图"]
[{"$nulls":21},"                  d、规划意见书和审定方案通知书及附图",{"$nulls":11},"a、建筑工程施工许可申请表一式两份"]
[{"$nulls":21},"                  e、绿地布置图（含现状古树、名木、大树保护方案）",{"$nulls":11},"b、建设用地规划许可证及附件"]
[{"$nulls":22},"园林报建（审批意见2003.05.20已取得）",null,"（30）",{"$nulls":7},"                       c、建设工程规划许可证及附件"]
[{"$nulls":32},"                      d、施工图纸设计文件审查通知书"]
[{"$nulls":21},"（22）","交通报建",null,"（31）",{"$nulls":7},"                     e、经备案的施工合同"]
[{"$nulls":32},"                     f、施工企业中标通知书"]
[{"$nulls":14},"             a、项目立项批复",{"$nulls":6},"                 a、规划意见书及附件",{"$nulls":10},"                     g、经备案的施工监理合同",{"$nulls":9},"a、工程竣工图"]
[{"$nulls":14},"            b、建设项目规划审批申报表",{"$nulls":6},"                   b、审定设计方案通知书",{"$nulls":6},"a、供电给水市政燃气热力意见",{"$nulls":3},"                    h、监理单位中标通知书",{"$nulls":8},"                        b、建筑工程消防设计审核意见书"]
[{"$nulls":14},"   c、《规划意见书》及附图一份",{"$nulls":6},"                     c、立项批复",{"$nulls":6},"b、建设项目规划审批报表",{"$nulls":3},"                    I、项目建设资金落实证明",{"$nulls":8},"                   c、消防验收申请"]
[{"$nulls":6},"       a、本单位报批函",{"$nulls":7},"            d、复审应持《修改设计方案通知书》",{"$nulls":4},"a、规划意见书",null,null,"d、交通影响评价报告",{"$nulls":4},"                                                                            c、审定设计方案通知书及审定的总平面图一份",{"$nulls":4},"                   j、年度施工计划",{"$nulls":8},"                d、建筑工程消防安全质量验收合格报告"]
[{"$nulls":6},"           b、项目建议书代可研报告",{"$nulls":7},"    e、标明用地钉桩成果以现状地形图",{"$nulls":3},"                       b、审定设计方案通知书两份",{"$nulls":3},"  e、市政道路方案及交通设施工程协议",{"$nulls":4},"                   d、建筑工程施工设计图纸",{"$nulls":4},"                  k、人防工程备案通知书",{"$nulls":3},"a、建设工程规划验收申请表演",{"$nulls":4},"             e、建设意见整改及落实情况"]
[{"$nulls":6},"            c、房地产开发企业资质证明文件",{"$nulls":7},"           为底图的总平面图",{"$nulls":3},"                     c、总平面图两份",{"$nulls":3},"     f、机械停车厂家设计文件及机械设备购货合同",{"$nulls":4},"                      e、工程档案登记证明",{"$nulls":4},"                  l、园林局伐移树木批准文件",{"$nulls":3},"       b、竣工图",{"$nulls":4},"          f、建筑防火材料构件和消防产品、设备合格证明、消防施工单位的资质证书"]
[{"$nulls":6},"                  d、中外合营项目合营各方签署的合作意向书",{"$nulls":7},"           f、各层平面图、各向立面图、剖面图",{"$nulls":7},"      g、交通组织流线分析图",{"$nulls":4},"                     f、按审定设计方案通知书要求取得的协议通知",{"$nulls":4},"                 m、四源费统一收费凭证",{"$nulls":3},"                 c、建设工程竣工测量成果报告"]
[{"$nulls":14},"   g、日照影响分析图及说明各一份",{"$nulls":7},"         h、平立剖面和车库坡道详图，住宅户型图和面积明细表",{"$nulls":7},"a、供电给水市政燃气意见",null,"                n、质量监督通知书",{"$nulls":3},"                       d、建设工程规划许可证",{"$nulls":4},"                       a、建设项目人防工程竣工验收备案表"]
[{"$nulls":14},"          h、交通影响评估报告",{"$nulls":3},"⒃","教育报建（审批意见2003.05.05已取得）",null,"（23）","签订公共配套协议书",null,"（36）",{"$nulls":4},"                       b、统计局意见",null,null,"                o、安全监督通知书",{"$nulls":9},"b、区县人防办出具的认可文件"]
[{"$nulls":7},"          a、建设项目地点征求意见函",{"$nulls":6},"        I、技术经济指标列表说明",{"$nulls":4},"30天（区教委）",null,null,"15天（区建委开发办）",{"$nulls":6},"                      c、散装水泥交费",null,null,"                p、建筑节能新型墙体收费凭证",{"$nulls":7},"人防验收",null,"c、人防工程竣工验收报告"]
[{"$nulls":7},"                b、建设项目规划审批申报表",{"$nulls":6},"        （如超出近控规应附控规调整审批通知书）",{"$nulls":6},"                   a、教育意见",{"$nulls":7},"                      d、墙体节能",null,null,"               q、散装水泥收费凭证",{"$nulls":7},"15天",null,"d、施工单位签署的人防工程质量保修书"]
[{"$nulls":7},"                     c、建设单位用地申请及拟建项目情况说明",{"$nulls":6},"         j、规划意见书要求应附的有关文件图纸和模型",{"$nulls":6},"                       b、规划意见书",{"$nulls":10},"               r、统计局登记通知",{"$nulls":7},"四方及电梯验收"]
[{"$nulls":7},"                           d、拟建方案设想总平面图",{"$nulls":6},"        k、单栋居住建筑规模和配套设施明细表一份",{"$nulls":6},"                          c、审定设计方案通知书",{"$nulls":18},"15天"]
[{"$nulls":8},"e、1：2000地形图一份",{"$nulls":5},"        l、人防、消防、园林、环保报告",{"$nulls":6},"                             d、总平面图",{"$nulls":9},"（47）","2003.0.15",{"$nulls":3},"2003.10.13",{"$nulls":3},"消防验收"]
[{"$nulls":21},"                                 e、召开公共配套协调会",{"$nulls":7},"2003.08.11",{"$nulls":4},"2003.08.20",{"$nulls":3},"2003.11.04",null,"17天"]
["建设工程","①",null,"②",null,"③",null,"④","⑤",null,"⑦",null,"⑩",null,"⒀",{"$nulls":3},"⒂",null,"⒅",null,null,"（29）",null,"（34）",null,"（40）",null,"（42）",null,null,"（48）",null,"（53）",null,"（55）",null,"（57）","（59）","规划验收",null,"（61）",null,"（63）",null,"（65）"]
[{"$nulls":40},"20天"]
[{"$nulls":32},"（49）",{"$nulls":7},"环保验收",{"$nulls":3},"              a、立项批复"]
[{"$nulls":25},"2003.06.30",null,"2003.07.25",{"$nulls":12},"教育验收",{"$nulls":3},"                b、法人资格证明"]
[{"$nulls":25},"2003.07.07",{"$nulls":6},"（50）",{"$nulls":7},"卫生验收",{"$nulls":3},"                 c、房屋竣工证明文件"]
[{"$nulls":13},"         a、项目立项批复",{"$nulls":26},"园林验收",{"$nulls":3},"                   d、房屋面积测量成果报告"]
[{"$nulls":13},"         b、农用地转用、征用建设项目用地申请书",{"$nulls":18},"（51）",{"$nulls":3},"                a、年度施工计划",null,null,"               a、建设项目环保审查审批手续（环保评估报告审批）",{"$nulls":4},"                     e、竣工项目地价款核准复函"]
[{"$nulls":13},"       c、《规划意见书》及附图一份和钉桩坐标成果通知单",{"$nulls":22},"                 b、施工合同",null,null,"              b、建设项目竣工环境保护验收、申请报告、验收申请表",{"$nulls":4},"                     f、公用建筑面积、分摊面积的材料"]
[{"$nulls":13},"     d、区县人民政府建设用地申请文件",{"$nulls":22},"                 c、地名办批复",null,null,"            c、建设项目环境保护验收监测报告",{"$nulls":4},"                        g、国有土地使用证或土地来源证明"]
[{"$nulls":13},"    e、土地利用总体规划对建设用地规模控制图",{"$nulls":22},"                  d、物业管理公约批复"]
[{"$nulls":13},"   f、一书四方案",{"$nulls":8},"（27）",null,"（33）",{"$nulls":11},"                   e、外商投资企业批准证书，企业成立合同，营业执照"]
[{"$nulls":13},"  g、补充耕地位置图及文字说明",{"$nulls":16},"2003.08.04",{"$nulls":5},"                    f、临时国有土地使用证，国有土地使用权出让合同，出门金缴纳证明"]
["用地手续",{"$nulls":4},"交地、场地平整（分期）",{"$nulls":4},"⑧","⑨","⑾",{"$nulls":4},"⒁",null,null,"⒆",null,"（24）",null,null,"（35）",null,null,"（41）",null,"（44）",{"$nulls":5},"                     g、建设工程规划许可证"]
[{"$nulls":31},"2003.08.04",{"$nulls":4},"                      h、建设工程施工许可证"]
[{"$nulls":13},"   h、建设用地勘测定界技术报告书及勘测定界图",{"$nulls":3},"            a、缴纳新增建设用地有偿使用费",null,null,"         a、立项批复",{"$nulls":4},"                a、项目立项批复",{"$nulls":5},"（45）",{"$nulls":4},"                       I、预售房价款监管协议书，投资总额达25%以上证明材料"]
[{"$nulls":13},"     I、拟占用土地1：10000幅土地利用现状图",{"$nulls":3},"              b、土地开垦费",null,null,"           b、建设项目规划审批表",{"$nulls":4},"                  b、办理土地出让手续申请",{"$nulls":10},"                        j、预售商品房面积测量报告和分摊部位的说明、各层平面图"]
[{"$nulls":13},"       j、建设拟征地土地权属情况汇总表",{"$nulls":3},"                c、防洪费",null,null,"            c、市政府征地批复",{"$nulls":4},"                   c、审定设计方案通知书",{"$nulls":10},"                          k、关于涉外项目国家安全审查的批复"]
[{"$nulls":13},"        k、省级土地行政主管部门对补充耕地的验收文件",{"$nulls":3},"                  d、菜田基金",null,null,"             d、用地钉桩成果",{"$nulls":4},"                    d、土地评估报告原件",{"$nulls":10},"                            l、市政府征地批复"]
[{"$nulls":13},"          l、新增建设用地有偿使用费准备情况的说明",{"$nulls":3},"                    e、超转费",null,null,"               e、按规划意见书要求取得的有关协议及批复文件",{"$nulls":4},"                     e、出让合同附图一式五份附图为钉桩图或审定设计方案通知书附图，原土地方国有土地使用证附图（加盖双方公章）",{"$nulls":10},"                            m、预售商品房型图，装修标准和设备简介"]
[{"$nulls":13},"            m、征地情况调查表",{"$nulls":3},"                      f、征地事务管理费",null,null,"                f、审定设计方案通知书",{"$nulls":4},"                      f、建设用地规划许可证及钉桩成果通知单"]
[{"$nulls":13},"              n、征地协议书",{"$nulls":3},"                        g、耕地占用税",{"$nulls":7},"                       g、建筑面积与用途说明"]
[{"$nulls":13},"                 o、？？城规划图",{"$nulls":3},"                          h、拆迁或土地补偿费",{"$nulls":7},"                         h、加盖工商部门备案章的营业执照复印件"]
[{"$nulls":25},"                         I、建设用地批准书或原用地单位的国有土地使用证、房屋所有权证、国有土地权属来源证明文件（原件）"]
[{"$nulls":21},"电信方案咨询",{"$nulls":3},"                           j、与原用地方签订的土地使用权及地上物补偿协议、联建协议及相关文件"]
[{"$nulls":21},"供电方咨询20天",{"$nulls":3},"                           k、房地产开发企业资质证书"]
[{"$nulls":21},"供水方案咨询20天",{"$nulls":3},"                            l、外经贸委核发的外商投资企业批准合作、合资企业合同、章程的批复",{"$nulls":6},"市政各口方案报装"]
[{"$nulls":32},"          20天"]
["市政工程",{"$nulls":7},"工作准备",{"$nulls":11},"（20）",null,null,"（28）","市政项目方案综合设计",null,"（37）","项目综合方案审定",null,"（43）",null,"（46）",null,"（52）",null,null,"（56）","市政各专业施工图设计",null,null,"（60）",null,"（62）",null,"（64）"]
[{"$nulls":21},"有线电视方案咨询20天",null,null,"         10人",null,null,"           15天",{"$nulls":6},"         10天",null,null,"30天"]
[{"$nulls":21},"道路方案咨询20天",{"$nulls":4},"                     a、建设项目规划审批报表",{"$nulls":6},"                   a、建设项目规划审批报表 "]
[{"$nulls":21},"热力方案咨询20天",{"$nulls":4},"                       b、市政项目综合方案",{"$nulls":6},"                     b、市政设计综合方案"]
[{"$nulls":26},"                          c、审定方案总图及道路方案",{"$nulls":6},"                       c、审定方案总图及道路方案"]
[{"$nulls":26},"                            d、市政各专业项目咨询方案",{"$nulls":6},"                         d、市政各专业项目咨询方案",{"$nulls":8},","]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}